## Table 1
Assignment No.:-01 (Div-A) Create Project Plan for Mobile App Development ▪ Specify project name and start (or finish) date. ▪ Identify and define project tasks. ▪ Define duration for each project task. ▪ Define milestones in the plan ▪ Define dependency between tasks ▪ Define project calendar. ▪ Define project resources and specify resource type ▪ Assign resources against each task and baseline the project plan 1. Project Name & Timeline  Project Name: Smart Mobile App Development  Start Date: August 1, 2025  Estimated End Date: November 30, 2025  Project Duration: 4 Months 2. Project Tasks, Durations & Dependencies
Task ID | Task Name | [5 empty] | Duration | Start Date | End Date | Dependencies
1 | Requirements Gathering | [5 empty] | 5 days | Aug 1, 2025 | Aug 7, 2025 | -
2 | Feasibility Study & Approval | [5 empty] | 3 days | Aug 8, 2025 | Aug 12, 2025 | 1
3 | UI/UX Design | [5 empty] | 10 days | Aug 13, 2025 | Aug 26, 2025 | 2
4 | Backend Architecture & Setup | [5 empty] | 7 days | Aug 27, 2025 | Sep 4, 2025 | 3
5 | Frontend Development | [5 empty] | 20 days | Sep 5, 2025 | Oct 2, 2025 | 3
6 | Backend Development | [5 empty] | 20 days | Sep 5, 2025 | Oct 2, 2025 | 4
7 | API Integration | [5 empty] | 7 days | Oct 3, 2025 | Oct 11, 2025 | 5.6
8 | Testing & QA | [5 empty] | 10 days | Oct 13, 2025 | Oct 24, 2025 | 7
Task ID | Task Name | [5 empty] | Duration | Start Date | End Date | Dependencies
9 | Bug Fixes & Optimization | [5 empty] | 7 days | Oct 27, 2025 | Nov 4, 2025 | 8
10 | User Acceptance Testing (UAT) | [5 empty] | 5 days | Nov 5, 2025 | Nov 11, 2025 | 9
11 | Deployment (App Store / Play Store) | [5 empty] | 3 days | Nov 12, 2025 | Nov 14, 2025 | 10
12 | Post-Deployment Support & Maintenance | [5 empty] | 10 days | Nov 17, 2025 | Nov 30, 2025 | 11
3. Milestones
Milestone ID |  |  | Description |  | Date
M1 |  |  | Project Kickoff |  | Aug 1, 2025
M2 |  |  | Design Completion |  | Aug 26, 2025
M3 |  |  | Development Completion |  | Oct 2, 2025
M4 |  |  | Testing Completed |  | Oct 24, 2025
M5 |  |  | App Deployed |  | Nov 14, 2025
M6 |  |  | Project Closure |  | Nov 30, 2025
4. Project Calendar
 Working Days: Monday to Friday  Working Hours: 9:00 AM to 6:00 PM  Holidays: Sundays and National Holidays (assumed 2 public holidays during the period)
5. Resources & Types
Resource Name |  |  |  | Type |  |  | Role
Project Manager |  |  |  | Human |  |  | Overall management
Business Analyst |  |  |  | Human |  |  | Requirements gathering
UI/UX Designer |  |  |  | Human |  |  | Wireframe and UI design
Backend Developer |  |  |  | Human |  |  | Backend coding and DB setup
Frontend Developer |  |  |  | Human |  |  | Frontend development
QA Engineer |  |  |  | Human |  |  | Testing and bug reporting
DevOps Engineer |  |  |  | Human |  |  | Deployment and CI/CD
Tools (Jira, GitHub, Figma) |  |  |  | Software Tool |  |  | Project & code management
6. Resource Assignment
Task ID | Task Name |  |  |  |  | Assigned Resources
1 | Requirements Gathering |  |  |  |  | Business Analyst, Project Manager
2 | Feasibility Study & Approval |  |  |  |  | Project Manager
3 | UI/UX Design |  |  |  |  | UI/UX Designer
Task ID |  | Task Name |  |  |  | Assigned Resources
4 |  | Backend Architecture & Setup |  |  |  | Backend Developer, DevOps Engineer
5 |  | Frontend Development |  |  |  | Frontend Developer
6 |  | Backend Development |  |  |  | Backend Developer
7 |  | API Integration |  |  |  | Backend & Frontend Developer
8 |  | Testing & QA |  |  |  | QA Engineer
9 |  | Bug Fixes & Optimization |  |  |  | All Developers, QA Engineer
10 |  | User Acceptance Testing (UAT) |  |  |  | Project Manager, QA Engineer
11 |  | Deployment |  |  |  | DevOps Engineer
12 |  | Post-Deployment Support |  |  |  | QA Engineer, Developers
7. Baseline the Project Plan
Baseline means finalizing the approved version of the schedule:
 Baseline Date: August 1, 2025  Version: Baseline V1.0  Approval by: Project Manager