## Table 1
Assignment No.:-01 (Div-B) Create Project Plan for Website Design ▪ Specify project name and start (or finish) date. ▪ Identify and define project tasks. ▪ Define duration for each project task. ▪ Define milestones in the plan ▪ Define dependency between tasks ▪ Define project calendar. ▪ Define project resources and specify resource type ▪ Assign resources against each task and baseline the project plan 1. Project Name & Timeline  Project Name: Responsive Business Website Design  Project Start Date: August 1, 2025  Planned Finish Date: September 15, 2025  Total Duration: 45 days
2. Project Tasks and Duration
Sr. | Task Name |  |  |  | Duration | Start Date | End Date
1 | Requirement Gathering |  |  |  | 3 days | Aug 1, 2025 | Aug 3, 2025
2 | Competitor Research |  |  |  | 2 days | Aug 4, 2025 | Aug 5, 2025
3 | Website Planning & Wireframing |  |  |  | 5 days | Aug 6, 2025 | Aug 10, 2025
4 | UI/UX Design |  |  |  | 7 days | Aug 11, 2025 | Aug 17, 2025
5 | Client Review & Approval (Design) |  |  |  | 2 days | Aug 18, 2025 | Aug 19, 2025
6 | Frontend Development (HTML/CSS/JS) |  |  |  | 10 days | Aug 20, 2025 | Aug 29, 2025
7 | Backend Development (CMS/Database) |  |  |  | 10 days | Aug 30, 2025 | Sep 8, 2025
8 | Testing & Bug Fixing |  |  |  | 4 days | Sep 9, 2025 | Sep 12, 2025
9 | Final Review & Deployment |  |  |  | 3 days | Sep 13, 2025 | Sep 15, 2025
3. Milestones
Milestone |  |  |  | Target Date
Requirements Finalized |  |  |  | August 3, 2025
Milestone |  |  |  | Target Date
Wireframe Completed |  |  |  | August 10, 2025
UI/UX Design Approved |  |  |  | August 19, 2025
Frontend Development Complete |  |  |  | August 29, 2025
Backend Completed |  |  |  | September 8, 2025
Website Go-Live |  |  |  | September 15, 2025
4. Dependencies Between Tasks
Dependent Task |  |  |  | Depends On
Competitor Research |  |  |  | Requirement Gathering
Website Planning & Wireframing |  |  |  | Competitor Research
UI/UX Design |  |  |  | Wireframing
Client Review |  |  |  | UI/UX Design
Frontend Development |  |  |  | Client Approval (Design)
Backend Development |  |  |  | Frontend Development
Testing & Bug Fixing |  |  |  | Backend Development
Final Review & Deployment |  |  |  | Testing Completed
5. Project Calendar
 Working Days: Monday to Saturday  Working Hours: 9 AM – 6 PM  Non-working Days: Sundays and public holidays
6. Resources & Resource Types
Resource Name |  | Role / Type
Project Manager |  | Management
Business Analyst |  | Functional
UI/UX Designer |  | Design
Frontend Developer |  | Technical
Backend Developer |  | Technical
QA Tester |  | Testing
Client |  | External Stakeholder
7. Resource Allocation
Task Name |  |  | Assigned Resource(s)
Requirement Gathering |  |  | Project Manager, Analyst
Competitor Research |  |  | Analyst
Wireframing |  |  | Analyst, UI/UX Designer
UI/UX Design |  |  | UI/UX Designer
Design Review |  |  | Client, Project Manager
Frontend Development |  |  | Frontend Developer
Backend Development |  |  | Backend Developer
Testing & Bug Fixing |  |  | QA Tester
Deployment |  |  | Project Manager, Developer
8. Baseline the Project Plan
 Save this initial plan as Baseline Plan v1.0  Use it to track actual vs. planned progress  Update with any changes and maintain a change log