## Table 1
Assignment No.:-02 (Div-A) Execute and Monitor Project Plan for Mobile App Development ▪ Update % Complete with current task status. ▪ Review the status of each task. ▪ Compare Planned vs Actual Status ▪ Review the status of Critical Path ▪ Review resources assignation status
Mobile App Development project, incorporating execution and monitoring elements:
Project Name: Mobile App Development | [7 empty] | Start Date: 2025-07- 15 |  |  | Finish Date: 2025-10- 15
Project Tasks Execution and Monitoring
Tas k ID | Task Name | Durati on (Days) |  | Star t Dat e | Plann ed Finish Date | Actua l Finish Date |  |  | Dependen cies | % Compl ete | Planne d vs Actual Status |  | Resourc es | Resour ce Type
1 | Project Initiation | 2 |  | 202 5- 07- 15 | 2025- 07-16 | 2025- 07-16 |  |  | - | 100% | On Schedu le |  | Project Manage r | Human
2 | Requirem ent Gathering | 5 |  | 202 5- 07- 17 | 2025- 07-21 | 2025- 07-22 |  |  | 1 | 100% | 1 Day Delay |  | Busines s Analyst | Human
3 | App Structure Planning | 3 |  | 202 5- 07- 23 | 2025- 07-25 | 2025- 07-26 |  |  | 2 | 100% | 1 Day Delay |  | UX Designe r | Human
4 | Design Phase | 10 |  | 202 5- 07- 27 | 2025- 08-05 | 2025- 08-06 |  |  | 3 | 100% | 1 Day Delay |  | UI Designe r, Graphic Designe r | Human
5 | Design Review and Approval | 4 |  | 202 5- 08- 07 | 2025- 08-10 | 2025- 08-11 |  |  | 4 | 100% | 1 Day Delay |  | Project Manage r, Client | Human
6 | Developm ent Phase | 20 |  | 202 5- 08- | 2025- 08-31 | In Progre ss |  |  | 5 | 75% | On Schedu le |  | Mobile App Develop | Human
Tas k ID | Task Name | Durati on (Days) |  | Star t Dat e | Plann ed Finish Date | Actua l Finish Date |  |  | Dependen cies | % Compl ete | Planne d vs Actual Status |  | Resourc es | Resour ce Type
|  |  |  | 12 | [8 empty] | er
7 | Content Creation | 10 |  | 202 5- 08- 20 | 2025- 08-30 | In Progre ss |  |  | 2 | 50% | On Schedu le |  | Content Writer | Human
8 | Integratio n and Testing | 7 |  | 202 5- 09- 01 | 2025- 09-07 | - |  |  | 6, 7 | 0% | Not Started |  | QA Tester | Human
9 | User Acceptanc e Testing (UAT) | 5 |  | 202 5- 09- 08 | 2025- 09-12 | - |  |  | 8 | 0% | Not Started |  | Client, QA Tester | Human
10 | Final Revisions | 4 |  | 202 5- 09- 13 | 2025- 09-16 | - |  |  | 9 | 0% | Not Started |  | Mobile App Develop er, UI Designe r | Human
11 | Deployme nt | 3 |  | 202 5- 09- 17 | 2025- 09-19 | - |  |  | 10 | 0% | Not Started |  | Mobile App Develop er | Human
12 | Project Closure | 2 |  | 202 5- 09- 20 | 2025- 09-21 | - |  |  | 11 | 0% | Not Started |  | Project Manage r | Human
Critical Path Review
 Critical Path Tasks: 1 → 2 → 3 → 4 → 5 → 6 → 8 → 9 → 10 → 11 → 12  Current Status: o Tasks 1 through 5 are completed, each with a 1-day delay. o Task 6 is 75% complete and on schedule. o Task 8 is dependent on the completion of Task 6 and has not started yet. Resource Assignation Status
Resource Name |  |  | Assigned Tasks |  |  |  | Current Task |  |  |  |  | Status
Project Manager |  |  | 1, 5, 12 |  |  |  | Monitoring & Coordination |  |  |  |  | Active
Business Analyst |  |  | 2 |  |  |  | Requirement Gathering |  |  |  |  | Completed
UX Designer |  |  | 3 |  |  |  | App Structure Planning |  |  |  |  | Completed
Resource Name |  |  | Assigned Tasks |  |  |  | Current Task |  |  |  |  | Status
UI Designer |  |  | 4, 10 |  |  |  | Final Revisions |  |  |  |  | Pending
Graphic Designer |  |  | 4 |  |  |  | Design Phase |  |  |  |  | Completed
Mobile App Developer |  |  | 6, 10, 11 |  |  |  | Development Phase |  |  |  |  | Active
Content Writer |  |  | 7 |  |  |  | Content Creation |  |  |  |  | Active
QA Tester |  |  | 8, 9 |  |  |  | Integration and Testing |  |  |  |  | Pending
Client |  |  | 5, 9 |  |  |  | Design Review & UAT |  |  |  |  | Pending
Summary
 Overall Status: The project is slightly behind schedule due to a series of 1-day delays in the initial tasks.  Critical Path Impact: The delays in early tasks have impacted the critical path, but ongoing tasks (6 and 7) are on schedule, which might help recover some lost time.  Resource Allocation: All resources are actively engaged or prepared for their upcoming tasks. The focus is on completing the Development Phase and Content Creation to proceed with Integration and Testing.
This table captures the on-going status and monitoring aspects of the Mobile App Development project, including % complete, task status, and comparisons of planned vs actual progress.