## Table 1
Assignment No.:-02 (Div-B)
Execute and Monitor Project Plan for Website Design project ▪ Update % Complete with current task status. ▪ Review the status of each task. ▪ Compare Planned vs Actual Status ▪ Review the status of Critical Path ▪ Review resources assignation status
The execution and monitoring plan for the Website Design project:
Project Name: Website Design Project | [7 empty] | Start Date: 2025-07-15 |  |  | Finish Date: 2025-10-15
Project Tasks Execution and Monitoring
Tas k ID | Task Name | Durati on (Days) |  | Star t Dat e | Plann ed Finish Date |  | Actua l Finish Date |  | Dependen cies | % Compl ete |  | Planne d vs Actual Status | Resourc es | Resour ce Type
1 | Project Initiation | 2 |  | 202 5- 07- 15 | 2025- 07-16 |  | 2025- 07-16 |  | - | 100% |  | On Schedu le | Project Manage r | Human
2 | Requirem ent Gathering | 5 |  | 202 5- 07- 17 | 2025- 07-21 |  | 2025- 07-22 |  | 1 | 100% |  | 1 Day Delay | Busines s Analyst | Human
3 | Site Structure Planning | 3 |  | 202 5- 07- 22 | 2025- 07-24 |  | 2025- 07-25 |  | 2 | 100% |  | 1 Day Delay | UX Designe r | Human
4 | Design Phase | 10 |  | 202 5- 07- 25 | 2025- 08-03 |  | 2025- 08-05 |  | 3 | 100% |  | 2 Days Delay | UI Designe r, Graphic Designe r | Human
5 | Design Review and Approval | 4 |  | 202 5- 08- 04 | 2025- 08-07 |  | 2025- 08-09 |  | 4 | 100% |  | 2 Days Delay | Project Manage r, Client | Human
6 | Developm ent Phase | 20 |  | 202 5- 08- 08 | 2025- 08-27 |  | In Progre ss |  | 5 | 70% |  | On Schedu le | Web Develop er, Backend Develop er | Human
Tas k ID | Task Name | Durati on (Days) |  | Star t Dat e | Plann ed Finish Date | Actua l Finish Date |  |  | Dependen cies | % Compl ete |  | Planne d vs Actual Status | Resourc es | Resour ce Type
7 | Content Creation | 10 |  | 202 5- 08- 28 | 2025- 09-06 | In Progre ss |  |  | 2 | 50% |  | On Schedu le | Content Writer | Human
8 | Integratio n and Testing | 7 |  | 202 5- 09- 07 | 2025- 09-13 | - |  |  | 6, 7 | 0% |  | Not Started | QA Tester | Human
9 | User Acceptanc e Testing (UAT) | 5 |  | 202 5- 09- 14 | 2025- 09-18 | - |  |  | 8 | 0% |  | Not Started | Client, QA Tester | Human
10 | Final Revisions | 4 |  | 202 5- 09- 19 | 2025- 09-22 | - |  |  | 9 | 0% |  | Not Started | Web Develop er, UI Designe r | Human
11 | Deployme nt | 3 |  | 202 5- 09- 23 | 2025- 09-25 | - |  |  | 10 | 0% |  | Not Started | Web Develop er | Human
12 | Project Closure | 2 |  | 202 5- 09- 26 | 2025- 09-27 | - |  |  | 11 | 0% |  | Not Started | Project Manage r | Human
Critical Path Review
 Critical Path Tasks: 1 → 2 → 3 → 4 → 5 → 6 → 8 → 9 → 10 → 11 → 12  Current Status: o Tasks 1 through 5 are completed, each with delays ranging from 1 to 2 days. o Task 6 is 70% complete and on schedule. o Task 8 is dependent on the completion of Task 6 and has not started yet. Resource Assignation Status
Resource Name |  |  | Assigned Tasks |  |  | Current Task |  |  |  |  | Status
Project Manager |  |  | 1, 5, 12 |  |  | Monitoring & Coordination |  |  |  |  | Active
Business Analyst |  |  | 2 |  |  | Requirement Gathering |  |  |  |  | Completed
UX Designer |  |  | 3 |  |  | Site Structure Planning |  |  |  |  | Completed
UI Designer |  |  | 4, 10 |  |  | Final Revisions |  |  |  |  | Pending
Graphic Designer |  |  | 4 |  |  | Design Phase |  |  |  |  | Completed
Resource Name |  |  | Assigned Tasks |  |  | Current Task |  |  |  |  | Status
Web Developer |  |  | 6, 10, 11 |  |  | Development Phase |  |  |  |  | Active
Backend Developer |  |  | 6 |  |  | Development Phase |  |  |  |  | Active
Content Writer |  |  | 7 |  |  | Content Creation |  |  |  |  | Active
QA Tester |  |  | 8, 9 |  |  | Integration and Testing |  |  |  |  | Pending
Client |  |  | 5, 9 |  |  | Design Review & UAT |  |  |  |  | Pending
Summary
 Overall Status: The project has experienced minor delays in the initial tasks but is generally progressing well.  Critical Path Impact: The delays in early tasks have impacted the critical path, but ongoing tasks (6 and 7) are on schedule, which might help recover some lost time.  Resource Allocation: All resources are actively engaged or prepared for their upcoming tasks. The focus is on completing the Development Phase and Content Creation to proceed with Integration and Testing.
This table captures the ongoing status and monitoring aspects of the Website Design project, including % complete, task status, and comparisons of planned vs actual progress.