## Table 1
Assignment No.:-03 (Div-A)
Generate Dashboard and Reports for Mobile App Development  Dashboard o Project Overview o Cost Overview o Upcoming Tasks  Resource Reports o Over-allocated Resources o Resource Overview  Cost Reports o Earned Value Report o Resource Cost Overview o Task Cost Overview  Progress Reports o Critical Tasks o Milestone Report o Slipping Tasks
Mobile App Development Dashboard and Reports
Dashboard
Project Overview
Metric |  |  | Value
Project Name |  |  | Mobile App Development
Start Date |  |  | 2025-07-15
Planned Finish Date |  |  | 2025-10-15
Actual Finish Date |  |  | In Progress
Current Status |  |  | On Schedule
% Complete |  |  | 65%
Cost Overview
Category |  | Planned Cost |  |  | Actual Cost |  |  |  |  | Variance
Total Cost |  | 100000 |  |  | 65000 |  |  |  |  | 35000
Resource Cost |  | 80000 |  |  | 52000 |  |  |  |  | 28000
Other Costs |  | 20000 |  |  | 13000 |  |  |  |  | 7000
Upcoming Tasks
Task ID | Task Name | [6 empty] | Start Date | [5 empty] | Due Date |  |  |  |  | Assigned To
8 | Integration and Testing | [6 empty] | 2025-09- 01 | [5 empty] | 2025-09- 07 |  |  |  |  | QA Tester
9 | User Acceptance Testing (UAT) | [6 empty] | 2025-09- 08 | [5 empty] | 2025-09- 12 |  |  |  |  | Client, QA Tester
10 | Final Revisions | [6 empty] | 2025-09- 13 | [5 empty] | 2025-09- 16 |  |  |  |  | Mobile App Developer, UI Designer
11 | Deployment | [6 empty] | 2025-09- 17 | [5 empty] | 2025-09- 19 |  |  |  |  | Mobile App Developer
Resource Reports
Over-allocated Resources
Resource Name |  |  |  | Assigned Tasks |  |  |  | Over-allocated Tasks
Mobile App Developer |  |  |  | 6, 10, 11 |  |  |  | None
Resource Overview
Resource Name |  |  |  | Role | [6 empty] | Current Task | [9 empty] | Status
Project Manager |  |  |  | Oversees project | [6 empty] | Monitoring & Coordination | [9 empty] | Active
Business Analyst |  |  |  | Gathers requirements | [6 empty] | Requirement Gathering | [9 empty] | Completed
UX Designer |  |  |  | Plans site structure | [6 empty] | App Structure Planning | [9 empty] | Completed
UI Designer |  |  |  | Creates UI designs | [6 empty] | Final Revisions | [9 empty] | Pending
Graphic Designer |  |  |  | Creates graphics | [6 empty] | Design Phase | [9 empty] | Completed
Mobile App Developer |  |  |  | Develops frontend | [6 empty] | Development Phase | [9 empty] | Active
Content Writer |  |  |  | Writes content | [6 empty] | Content Creation | [9 empty] | Active
QA Tester |  |  |  | Conducts testing | [6 empty] | Integration and Testing | [9 empty] | Pending
Client |  |  |  | Provides approval | [6 empty] | Design Review & UAT | [9 empty] | Pending
Cost Reports
Earned Value Report
Metric |  |  |  | Value
Planned Value (PV) |  |  |  | 70000
Earned Value (EV) |  |  |  | 65000
Actual Cost (AC) |  |  |  | 65000
Schedule Variance (SV) |  |  |  | -5000
Cost Variance (CV) |  |  |  | 0
Resource Cost Overview
Resource Name |  |  |  | Planned Cost |  |  | Actual Cost | [5 empty] | Variance
Project Manager |  |  |  | 10000 |  |  | 8000 | [5 empty] | 2000
Business Analyst |  |  |  | 8000 |  |  | 7000 | [5 empty] | 1000
UX Designer |  |  |  | 12000 |  |  | 12000 | [5 empty] | 0
Resource Name |  |  |  | Planned Cost |  |  | Actual Cost | [5 empty] | Variance
UI Designer |  |  |  | 15000 |  |  | 12000 | [5 empty] | 3000
Graphic Designer |  |  |  | 10000 |  |  | 10000 | [5 empty] | 0
Mobile App Developer |  |  |  | 20000 |  |  | 15000 | [5 empty] | 5000
Content Writer |  |  |  | 5000 |  |  | 3000 | [5 empty] | 2000
QA Tester |  |  |  | 10000 |  |  | 5000 | [5 empty] | 5000
Client |  |  |  | 0 |  |  | 0 | [5 empty] | 0
Task Cost Overview
Task ID | Task Name | [7 empty] | Planned Cost | [5 empty] | Actual Cost |  |  |  |  | Variance
1 | Project Initiation | [7 empty] | 2000 | [5 empty] | 1500 |  |  |  |  | 500
2 | Requirement Gathering | [7 empty] | 5000 | [5 empty] | 4000 |  |  |  |  | 1000
3 | App Structure Planning | [7 empty] | 4000 | [5 empty] | 3500 |  |  |  |  | 500
4 | Design Phase | [7 empty] | 10000 | [5 empty] | 8500 |  |  |  |  | 1500
5 | Design Review and Approval | [7 empty] | 3000 | [5 empty] | 2500 |  |  |  |  | 500
6 | Development Phase | [7 empty] | 30000 | [5 empty] | 20000 |  |  |  |  | 10000
7 | Content Creation | [7 empty] | 5000 | [5 empty] | 3000 |  |  |  |  | 2000
8 | Integration and Testing | [7 empty] | 8000 | [5 empty] | 4000 |  |  |  |  | 4000
9 | User Acceptance Testing (UAT) | [7 empty] | 5000 | [5 empty] | 0 |  |  |  |  | 5000
10 | Final Revisions | [7 empty] | 5000 | [5 empty] | 0 |  |  |  |  | 5000
11 | Deployment | [7 empty] | 3000 | [5 empty] | 0 |  |  |  |  | 3000
12 | Project Closure | [7 empty] | 2000 | [5 empty] | 0 |  |  |  |  | 2000
Progress Reports
Critical Tasks
Task ID | Task Name | [7 empty] | Planned Finish Date | [8 empty] | Actual Finish Date |  |  |  |  | Status
1 | Project Initiation | [7 empty] | 2025-07-16 | [8 empty] | 2025-07-16 |  |  |  |  | Completed
2 | Requirement Gathering | [7 empty] | 2025-07-21 | [8 empty] | 2025-07-22 |  |  |  |  | Completed
3 | App Structure Planning | [7 empty] | 2025-07-25 | [8 empty] | 2025-07-26 |  |  |  |  | Completed
4 | Design Phase | [7 empty] | 2025-08-05 | [8 empty] | 2025-08-06 |  |  |  |  | Completed
5 | Design Review and Approval | [7 empty] | 2025-08-10 | [8 empty] | 2025-08-11 |  |  |  |  | Completed
6 | Development Phase | [7 empty] | 2025-08-31 | [8 empty] | In Progress |  |  |  |  | On Schedule
8 | Integration and Testing | [7 empty] | 2025-09-07 | [8 empty] | - |  |  |  |  | Not Started
9 | User Acceptance Testing (UAT) | [7 empty] | 2025-09-12 | [8 empty] | - |  |  |  |  | Not Started
10 | Final Revisions | [7 empty] | 2025-09-16 | [8 empty] | - |  |  |  |  | Not Started
11 | Deployment | [7 empty] | 2025-09-19 | [8 empty] | - |  |  |  |  | Not Started
12 | Project Closure | [7 empty] | 2025-09-21 | [8 empty] | - |  |  |  |  | Not Started
Milestone Report
Milestone | [5 empty] | Planned Date | [5 empty] | Actual Date |  |  |  | Status
Project Kickoff | [5 empty] | 2025-07-15 | [5 empty] | 2025-07-15 |  |  |  | Completed
Requirement Document | [5 empty] | 2025-07-21 | [5 empty] | 2025-07-22 |  |  |  | Completed
Milestone | [5 empty] | Planned Date | [5 empty] | Actual Date |  |  |  |  | Status
Site Map Created | [5 empty] | 2025-07-25 | [5 empty] | 2025-07-26 |  |  |  |  | Completed
Initial Design Completed | [5 empty] | 2025-08-03 | [5 empty] | 2025-08-06 |  |  |  |  | Completed
Design Approved | [5 empty] | 2025-08-07 | [5 empty] | 2025-08-11 |  |  |  |  | Completed
Frontend and Backend Completed | [5 empty] | 2025-08-31 | [5 empty] | - |  |  |  |  | In Progress
Content Ready | [5 empty] | 2025-09-06 | [5 empty] | - |  |  |  |  | In Progress
Testing Completed | [5 empty] | 2025-09-13 | [5 empty] | - |  |  |  |  | Not Started
UAT Completed | [5 empty] | 2025-09-18 | [5 empty] | - |  |  |  |  | Not Started
Revisions Completed | [5 empty] | 2025-09-22 | [5 empty] | - |  |  |  |  | Not Started
Site Live | [5 empty] | 2025-09-25 | [5 empty] | - |  |  |  |  | Not Started
Project Completed | [5 empty] | 2025-09-27 | [5 empty] | - |  |  |  |  | Not Started
Slipping Tasks
Task ID | Task Name | [5 empty] | Planned Finish Date | [8 empty] | Actual Finish Date | [5 empty] | Status |  | Delay
2 | Requirement Gathering | [5 empty] | 2025-07-21 | [8 empty] | 2025-07-22 | [5 empty] | Completed |  | 1 Day
3 | App Structure Planning | [5 empty] | 2025-07-25 | [8 empty] | 2025-07-26 | [5 empty] | Completed |  | 1 Day
4 | Design Phase | [5 empty] | 2025-08-05 | [8 empty] | 2025-08-06 | [5 empty] | Completed |  | 1 Day
5 | Design Review and Approval | [5 empty] | 2025-08-10 | [8 empty] | 2025-08-11 | [5 empty] | Completed |  | 1 Day
This table captures the detailed status and monitoring elements of the Mobile App Development project, including dashboards for project overview, cost overview, and upcoming tasks, as well as various resource, cost, and progress reports.